## Informations
General Information
The Product Backlog total number of SP may vary from sprint to sprint if some US are added or deleted, or if some US are not accepted in a precedent sprint and that they have to be taken again and modified in the next sprint.
It is therefore necessary to manually sum that total of SP at the end of every sprint and update the Release Roadmap
Every day, it is necessary to update the remaining hours estimation related to the tasks of the sprint. That estimation may increase if one thinks that it would take more time than expected.
There is the definition of Done with the list of actions that the team decided to achieve and the definition of done done where the PO has to decide if the done US are ok for him.
Reminder on the work process concerning the PB
1. Description mockup and description of the user acceptance tests by the PO
2. Evaluation of the SP by the team + 30 min / week for re-evaluating it
3. Priorization by the PO (MOSCOW by example or business value, …)
4. Sprint planning phase 1 where the Dev team choose roughly the number of SP that it thinks could be accomplished during the next sprint + split of too big US
5. Sprint planning phase 2 with split in tasks of the current sprint US + estimation in hours
At the bottom of each tab you will find additional information about the objectives of the tab
The Informations tab gives general recommandations about the process to follow in Scrum, especially concerning the way to plan the User Stories with the Product Owner during the Sprint Planning events
Globally you need to have followed a Scrum course to be able to understand this file and the inherent concepts.

## Vision
General information about the project
Add the context, objectives and Mockups or any other information useful for understanding the vision of the PO
Information
The Vision tab allows the developers to centralize the description of the project, including the general vision, screen copies of the mockups of the different user interfaces , as well as business canvas when appropriate.

## User Roles
Rôles | Personas | Description
End-User | Mary | Secretary in a bank, …
Developper
Marketing
Information
In Scrum it is important to understand in details who will use the delivered software in order to develop good and useful functionalities for them.
In this tab we don't just specify that a "User" will use it, we try to be more specific by writting the type of job of that user and even, if possible, the type of persona this user has.
Like that the developer can use empathy and put himself at the place of that person when developping his or her functionalities.

## ProductBacklog
US Nr. | Theme | As an/a … | I want to … | so that … | Acceptance Criteria | Priority | Status | Story Points | Sprint | US accepted (done done) | MoSCoW
1 | Preparation | Developer | Prepare the work environment | I can share my code with the team | Environment working + all members have all accesses + know how to use | 1000 | 3 | 3 | 0 | 2024-04-24 | Must
2 | Research | Developer | Draw mockups | I can have a better overview of the application |  | 950 | 3 | 5 | 0 | 2024-04-24 | Must
3 | Preparation | Developer | Create the Product Backlog | We can have a list of all the tasks |  | 900 | 3 | 5 | 0 | 2024-04-24 | Must
4 | Preparation | Developer | Have contact with the product owner | We can have a clear understanding of the tasks and the project |  | 850 | 3 | 1 | 0 | 2024-04-24 | Must
5 | Application | User | Access to the welcome page | I can show one data from the DB on the screen |  | 800 | 3 | 1 | 0 | 2024-04-24 | Must
11 | Application | User | Synchronize data | I see always the most updated data | I can see the logo when the app starts and a message telling if the sync was ok or not + button to force sync | 750 | 3 | 13 | 1 | 2024-05-08 | Must
22 | Website | Admin | Add, delete or edit the news | I can provide an updated list |  | 700 | 1 | 13 | 1 |  | Must
8 | Application | User | Schedule a personal program | I can customize my own program |  | 650 | 3 | 5 | 1 | 2024-05-08 | Must
23 | Website | Admin | Adapt the program and the other pages | I can update the app |  | 600 | 3 | 5 | 1 | 2024-05-08 | Must
6 | Application | User | Read news of the conferences | I know the latest infos about changes, additional speakers, new data, etc. |  | 550 | 3 | 5 | 1 | 2024-05-08 | Must
22 | Website | Admin | Add, delete or edit the news (FORMER REJECTED) | I can provide an updated list |  | 500 | 3 | 3 | 2 | 2024-05-08 | Must
7 | Application | User | See the list of the conferences | I can know several informations about conferences (date - rooms - etc.) |  | 450 | 3 | 5 | 2 | 2024-05-22 | Must
9 | Application | User | Display an "about" page | I can know who has done this amazing app |  | 400 | 3 | 2 | 2 | 2024-05-22 | Must
10 | Application | User | Have information about all speakers | I can know their skills |  | 350 | 3 | 5 | 2 | 2024-05-22 | Must
14 | Application | User | Display a "partners" page | I can see who sponsorize this conference |  | 300 | 3 | 3 | 2 | 2024-05-22 | Must
15 | Application | User | Display an "organisers" page | I can see informations about the organisers |  | 250 | 3 | 3 | 2 | 2024-05-22 | Must
12 | Application | User | Have a map to find the site | I can reach the UNIL directly |  | 200 | 3 | 13 | 2 | 2024-05-22 | Must
19 | Application | User | Search inside the app | I can find any conference or speaker diretly |  | 190 | 3 | 13 | 2 | 2024-05-22 | Must
24 | Application | Admin | Publish my app on the Play Store | everyone can donwload it |  | 180 | 3 | 5 | 3 | 2024-06-05 | Must
13 | Application | User | See an internal map | I never get lost inside the building |  | 170 | 3 | 1 | 3 | 2024-06-05 | Must
16 | Application | User | Choose some parameters on a "settings" page | I can customize PUSH notifications |  | 160 | 3 | 13 | 3 | 2024-06-05 | Must
17 | Application | User | Share conference with Twitter and email | I can inform my friends about it |  | 150 | 3 | 13 | 3 | 2024-06-05 | Should
18 | Application | User | Leave a feedback | I can inform the developers about problems or misunderstandings in the app |  | 140 | 3 | 5 | 3 | 2024-06-05 | Should
21 | Application | User | Have a nice design and user experience | it is nicer to use the app |  | 130 | 3 | 8 | 3 | 2024-06-05 | Should
22 | Application | User | US description | … |  | 120 | 3 | 13 | 4 |  | Should
23 | Application | User | US description | … |  | 110 | 3 | 5 | 4 |  | Should
24 | Application | User | US description | … |  | 100 | 3 | 3 | 4 |  | Should
25 | Application | User | US description | … |  | 95 | 3 | 13 | 4 |  | Should
26 | Application | User | US description | … |  | 90 | 3 | 5 | 4 |  | Should
27 | Application | User | US description | … |  | 85 | 3 | 3 | 4 |  | Should
28 | Application | User | US description | … |  | 80 | 0 | 13 | 5 |  | Should
29 | Application | User | US description | … |  | 75 | 0 | 21 | 5 |  | Should
30 | Application | User | US description | … |  | 70 | 0 | 13 | 5 |  | Should
31 | Application | User | US description | … |  | 65 | 0 | 13 | 5 |  | Should
40 | Application | User | Change the language of the app | I can better understand if I do not speak English | optional (not mandatory) | 10 | 0 |  |  |  | Won't
0
0
Totaux | [5 empty] | Total SP |  | 250
Note on G2: the priorisation technique MoSCoW: 1.Must have (fundamental feature) 2.Should have (important but short-term workaround available) 3.Could have (can be let out of the realease if time runs out) 4.Won't have this time (later release)
Note on H2: Enter 1, 2 or 3 and the satus is automaticaly displayed (blue = todo, yellow = in progress, green = done and accepted, red= rejected) The task is considered as 'done':3 when all points decided in team are solved (example of done definition : documentation in code, unittests passed, functional tests passed, user manual completed, …)

## Release Roadmap - Velocity
Sprints
| 0 | 1 | 2 | 3 | 4 | 5
Nb SP planned | 15 | 41 | 47 | 45 | 42 | 0
Todo | 216 | 178 | 131 | 86 | 44
Done | 15 | 28 | 47 | 45 | 42
Rejected | 0 | 13 | 0 | 0 | 0
Realized Cum. | 15 | 43 | 90 | 135 | 177
Average |  | 28 | 37.5 | 40 | 40
In the table above, replace formulas with real numbers
from the product backlog.
[7 empty] | Blue line | Number of SP for all functionalities to implement
[7 empty] | Green line | Number of Accepted SP
Information
This Tab contains some visual tables and graphs showing how the project is going on. For each sprint we fill the number of total Story Points remaining at the begginning of it, the number of Story Points "done" at the end of the sprint and the number of rejected Story Points.
Then the project velocity graph shows how many User Stories the Team is able to complete per sprint, with a dynamic average. Note that in the initial sprint, when the team has to prepare the working environment, only the "one", Story Point User Story needs to be done. It will be used afterwards to compare with the other User Stories.
The Release Roadmap graph shows the main indicators and allows to quickly answer how many sprint will be necessary to finish all the todos.
Note on B3: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : - Min 1 US of 1 SP like a Hello World - You should reach the build artifact.
Note on A5: Number of SP at the end of each sprint. That total of SP will change at each sprint

## Sprint 0
| User stories |  | Sprint | 0
1 | Prepare the work environment |  | Start date | 2024-04-19
2 | Draw mockups |  | End date (included) | 2024-04-23
3 | Create the Product Backlog |  | Sprint goal | Prepare all the environment to be ready to develop the project
4 | Have contact with the product owner |  | Nbre working days | 5
5 | Access to the welcome page
TRAVAIL RESTANT A FAIRE - PAS TRAVAIL DEJA EFFECTUE
ID US.task | Task Name | Resp. | Initial Estimate |  | Day 01 (19.04.2024) | Day 02 (20.04.2024) | Day 03 (21.04.2024) | Day 04 (22.04.2024) | Day 05 (23.04.2024)
1.1 | Prepare the work environment | Joe | 3 |  | 3 | 0 | 0 | 0 | 0
1.2 | Analysing another app | Alex | 2 |  | 2 | 0.5 | 0 | 0 | 0
1.3 | Documentation | Joe | 6 |  | 6 | 3 | 3 | 1 | 0
1.4 | Research Android/Java | Joe | 6 |  | 6 | 3 | 3 | 3 | 2
2.1 | Mockups Thinking | Fabrice | 1 |  | 1 | 1 | 1 | 0 | 0
2.2 | Mockups and prototypes desingning | Alex | 6 |  | 6 | 6 | 3 | 3 | 1
3.1 | Create the Product Backlog | Fabrice | 3 |  | 3 | 3 | 0 | 0 | 0
4.1 | Meeting with PO | Joe | 2 |  | 2 | 0 | 0 | 0 | 0
5.1 | Create one simple table in the DB | Alex | 2 |  | 2 | 2 | 2 | 0 | 0
5.2 | Service code to retrieve data from DB | Fabrice | 1 |  | 1 | 1 | 1 | 1 | 0
5.3 | Display on Android Screen | Joe | 2 |  | 2 | 2 | 2 | 2 | 0
|  | Total | 34
|  | Remaining | 34 |  | 34 | 21.5 | 15 | 10 | 3
|  | Theoretical |  |  | 34 | 25.5 | 17 | 8.5 | 0
Impediments
[8 empty] | Sample impediment |  | statut
[8 empty] | PO not available even by email |  | Solved on Day 04
Information
This tab contains the sprint backlog, or all the information concerning a specific sprint. We initially set the number of the current sprint, and its goal. Then it contains the list of User Stories chosen by the Team to enter this sprint. We have to modify the different elements like dates, number of working days, number of columns in the table to match with the actual context of the sprint.
The "initial sprint estimation" field contains the number of story points decided to enter this sprint.
Then the team has to split all the User Stories into tasks, add a unique id to each task by following this rule : the initial number corresponds to the ID of the user story, followed by a point, and the second number, which is the number of the task.
When the team will do his daily meetings, every member could then decide which task he will become responsible of. Even if there is only one responsible per task, it's the whole team who has the global responsibility to reach the sprint goal. Therefore there may be more than one person working on a task.
The estimations are done in hours for the tasks, which are smaller than the user stories they belong, and therefore more precise.
In the Burndown chart, which shows the number of remaining hours, the red and blue lines have to start at the same position, as at the beginning of the first day of the sprint the theoretical and real number of hours are the same.
Note on E5: Modify the table below and Burndown chart according to the number of working days
Note on D8: Auteur: This is the team's initial assessment of how much work is needed to implement this task. The unit is hours. This part must be filled by developers only. Not by the product owner
Note on F8: The first day of the sprint you start at 8 o'clock therefore the remaining effort is the same as the initial estimate
Note on D21: Auteur: Initial total of Scrum units

## Done Definition
DONE DEFINITION FOR ALL USER STORIES
Documented in the code and in the user guide and technical guides
Code commited on GIT
Unit tests tested by peer developper
Acceptance Criteria passed
Information: The definition of done tab contains an evolutive list of tasks that the team has to perform after completing each user story, in order to maximize the global quality of the code and his work.

## DailyMeeting
Sprint | When | Who | What did you do since last time? | What will you work on today? | Do you have any obstacles?
0 | 14.11.2019 | Jean-Marie | Inform yourself about the project and organize yourself within the team / Started with the ProductBacklog | Create database schema | -
|  | Agron | Inform yourself about the project and organize yourself within the team / Started with the ProductBacklog | Discuss Jean-Marie's database schema / Create mockups | -
|  | David | Sick
|  | Yannick | Jeunesse and sport
|  | Damian | Inform yourself about the project and organize yourself within the team / Existing app analyzed / Android project viewed from last semester | Discuss Jean-Marie's database schema / Create mockups | understand all US stories
0 | 15.11.2019 | Jean-Marie | Database schema created / Github created | Define Storypoints / Revise database schema | -
|  | Damian | First mockups created | Define Storypoints / Create Mockups | define the right mockup-size
|  | David | Working on the ProductBacklog / Setting up OneDrive | Define Storypoints / Create Mockups | -
|  | Yannick | Working on the ProductBacklog | Define Storypoints / Complete ProductBacklog | -
|  | Agron | Module Data Mining Presentation
1 | 18.11.2019 | Jean-Marie | Finishing the creation of the Database schema | Retrospective / Questionning
|  | David | Creating Mockups / Verifying storypoints | Retrospective / Questionning
|  | Damian | Creating Mockups / Verifying storypoints | Retrospective / Questionning / Disscus Mockups
|  | Agron | Creating Mockups / Verifying storypoints | Retrospective / Questionning
|  | Yannick | Working on the backlog file / Verifying storypoints | Retrospective / Questionning / Finish backlog file
1 | 21.11.2019 | Meeting with the PO
1 | 22.11.2019 | Jean-Marie | Finalizing the mockups, create some navigation logic, connected the project to Firebase | Correct the Data model, thinking about how to code together
|  | David | Absent | Absent
|  | Damian | Discussed mockups and navigation, talk with the PO | Start with the code, but before try to split the work
|  | Agron | Mockups | Correct the transport detail page
|  | Yannick | Not here last time | Discuss the way we code, start coding today.
1 | 25.11.2019 | Jean-Marie | Create the Transport Page form (whithout data) | Correct the data model, implement the live data and repositories for at least order and checkpoints
|  | Agron | Transport List skeletton (no data yet), Photo screen, Signature screen started | finish the signature screen
|  | David | Profile page skeletton (no data yet) | work on the profile page and manifest
|  | Yannick | Navigation, the navigation document | Start user and technical guide
|  | Damian | Entities structure needed for sprint 1 | Update the entities, look for the exclude things, repositories and live data
1 | 28.11.2019 | Jean-Marie | Retrieve data from the db to the transportList and transportDetail page | Create the Json file for the initial demo data
|  | David | Finalize the userList layout and navigation | Revise userList page and correct errors
|  | Agron | Signature screen closed | modifiy the button add on the transport list page, insert a order
|  | Damian | LiveData classes created, @Exclusion notation read | Create spinner to select driver and products
|  | Yannick | Started the user guide and technical guide | updating the backlog file
1 | 29.11.2019 | Jean-Marie | Updated db schema, created test data in json, implemented transoprt list. implemented transport details. | Create function to change the status of an order
|  | David | Correcting bugs and starting implementation of data and still have problem on foreign keys | Continue the data implementation | Foreign key are terrible to deal with in firebase
|  | Agron | Add function was created but with some small bugs | Debug the Add function and create the Edit function
|  | Damian | Spinner was created | Get data from the database, delete-order function | Get data from the DB because we assigned a key and not an automatic key was added by Firebase
|  | Yannick | Absent | Absent
2 | 2019-12-02 | Demo / Review Sprint 1
|  | All | Sprint 1 finished | Define US for the next sprint (2)
2 | 2019-12-05 | All / No course
2 | 2019-12-06 | All | No DailyMeeting, because Damian and Agron were missing due to another subject (meeting Bern) and we had no time on Thursday to create a project.
2 | 2019-12-09 | Damian | Add product, display it in the spinner. Checkpoints (fill it with order and update it). Display it in the order. | Look for bugs on the code. Get the current gps position + checkpoint type spinner, change the style of the checkpointslist
|  | JM | Client list, customer list, retreive data from the db | Add a customer
|  | David | Retreive data for the profile, monthly report | Retreive id of the user when login, fill the db with real data to have an overview
|  | Yannick | Bike validation page, documentation | Try to deploy the app
|  | Agron | Absent | Absent
2 | 2019-12-12 | Damian | fixed the bugs, get the current gps location, add checkpoint-type spinner by adding a checkpoint | test the gps-location, work on the logic for update the status of an order
|  | JM | add a client to the list an select this to the order | update the status of an order
|  | David | updated the DB, fill this with real data | work an the monthly report
|  | Yannick | deploying of the app | work on the documentation
|  | Agron | fixed the bugs with the login | Registerpage with all logic
2 | 2019-12-13 | JM | Implemented status logic | Finish the train station checkpoint. We also forgot that a checkpoint has a timestamp when created, but it also needs a timestamp once the package is picked up again.
|  | Yannick | Documentation - Bike confirmation | Change the json file into a csv in the monthly report
|  | Damian | thinking about the status of the orders, discussing with Stefan | Display all users in a spinner (add order) and filter the orthers by the users
|  | David | Retrieve the data for the user from the db, add a loading page for the profile when the db take time to answer. | Retrieve the foreign key for the address and work on the monthly report page
|  | Agron | absent
Information
The Daily Meeting tab should contain the answers to the three questions: What did I do since last time, what will I do today, and, Did I meet any problems in my tasks. This meeting should last maximum 15 min every full day of work.

## Retroperspective
SPRINT 0
End : 18.11.2019
Name | What went Good ? | What went Wrong ? | How to improve ?
Yannick | - | He doesnt't understand all user-stories | -
Jean-Marie | It was good, which one is a expert in one topic so he take this tasks | They weren't all there | notify the team members when he as an appointment
David | need all informations of the customer and understand this | - | -
Agron | Tell a lot with the teammembers, split the task | be at the time in the school | -
Damian | good beginning, task splitting, better understanding of the user stories. | - | -
SPRINT 1
End : 02.12.2019
Name | What went Good ? | What went Wrong ? | How to improve ? | General feedback / Sprint Review
Yannick | Able to reach the goal | Communication can still be better | Explain more what we do / are going to do | - Keep it simple / Don't waste time on unimportant things
Jean-Marie | We've reached the goal and faced the first difficulties, which will help us in the future | Coordination and lack of implication | Define tasks earlier and assign them to people equaly. | - Sort orders by date and time
David | We were able to fullfil most of the tasks and reach the fixed goals | We still need to communicate more | Talk more together | - History by delete an order / Rename deletebutton -> cancel
Agron | The goals were reached and important information e.g. for the code conventions are declared | The punctuality has improved but it can be better and the tasks should be done by that person, who is responsible for that | Maybe tallk together or set deadlines and write the tasks down | - Demo: Better to explain a US then demo, then the next US and the demo and so on
Damian | Almost all US could be successfully implemented, programming convention were defined, so that all program in the same style, good planning, so that all understood the mission well | distribution of tasks | Write down each person's tasks. Everyone should have completed the tasks by the agreed deadline. | - In the next sprint the rider should be in focus / The app should be seen as the rider's point of view
- Good that the whole concept (welcomepage) has already been implemented, because so you can see how it will look at the end
SPRINT 2
End : 13.12.2019
Name | What went Good ? | What went Wrong ? | How to improve ? | General feedback / Sprint Review
Yannick | Good job | More comitment for the group meeting / documentation part, it is note only coding and it is not the scrum master part to do everything in the documentation part |  | - good Demo / Presentation
Jean-Marie | We were able to easily tu our codes together | Some team members have done their job at the last moment. This made it difficult to organize and stressful. | Start working faster. | - Handling with the checkpoints is nice
David | All the functionnalities were developped and a good collaboration was done | No need to optimize, do as easy as possible however it's not the most optimized | Assume that we need to developp fast and optimize later | - In the next sprint, the accountant should be In focus / clean all bugs
Agron | We have done all the defined US and we have also well seperated teh tasks | Some troubles with the OneDrive for our product backlog | Maybe to have always a plan b | -When logging in to Google, the password should always be requested when logging in, i.e. do not save the password.
Damian | We were able to implement the defined US successfully. We had a better division of tasks than in Sprint 1. The communication between the developers was good. | We once had a problem with the OneDrive file, so when the Product Owner met us, the Sprint2 sheet was not uptodate. | A copy of the ProductBacklog should be available online. | -We will receive a list with all important attributes for the accountant from the PO.
-On the LoginPage the fields e-mail address and password should not be filled in automatically.
-It was good that we had published a current version in the store. Update it from time to time.
Information
The retrospective tab contains the summary of the discussions of the team during the retrospective event, at the end of every sprint. Everyone should speak and answer the questions: What went good? What went wrong? What should be improved?

## Student1 Journal
Name | Date | What | Time | Type | Total hours
| 2023-09-23 | Meeting avec les Product Owner et le Coach | 2:00 | Meeting | 17:00 | The goal of this journal is that each student writes the work done with its respective time spent.
| 2023-09-23 | Installation outils et composants requis | 2:00 | Preparation |  | This formally not asked by SCRUM, but useful to monitor the work of each student in the team.
| 2023-09-23 | Clone des projets Git fournis par les Product Owner | 2:00 | Preparation |  | Here are some example lines of the journal to illustrate it.
| 2023-09-30 | Daily Meeting | 0:30 | Meeting
| 2023-09-30 | Récupération du projet de base et tenter de le faire fonctionner | 2:00 | Preparation
| 2023-10-01 | Ajout du networking au projet avec un script pour tester | 2:00 | Dev
| 2023-10-07 | Daily Meeting + planning poker | 1:30 | Meeting
| 2023-10-14 | Daily Meeting | 2:00 | Meeting
| 2023-10-14 | Possibilité de tester plusieurs joueurs ajout d'interface pour se connecter en server, host,... debuguer le problème | 3:00 | Dev
etc. etc. etc.

## Student2 Journal
Name | Date | What | Time | Type | Total hours
| 2023-09-23 | Meeting avec les Product Owner et le Coach | 2:00 | Meeting | 17:00 | The goal of this journal is that each student writes the work done with its respective time spent.
| 2023-09-23 | Installation outils et composants requis | 2:00 | Preparation |  | This formally not asked by SCRUM, but useful to monitor the work of each student in the team.
| 2023-09-23 | Clone des projets Git fournis par les Product Owner | 2:00 | Preparation |  | Here are some example lines of the journal to illustrate it.
| 2023-09-30 | Daily Meeting | 0:30 | Meeting
| 2023-09-30 | Récupération du projet de base et tenter de le faire fonctionner | 2:00 | Preparation
| 2023-10-01 | Ajout du networking au projet avec un script pour tester | 2:00 | Dev
| 2023-10-07 | Daily Meeting + planning poker | 1:30 | Meeting
| 2023-10-14 | Daily Meeting | 2:00 | Meeting
| 2023-10-14 | Possibilité de tester plusieurs joueurs ajout d'interface pour se connecter en server, host,... debuguer le problème | 3:00 | Dev
etc. etc. etc.

## Student3 Journal
Name | Date | What | Time | Type | Total hours
| 2023-09-23 | Meeting avec les Product Owner et le Coach | 2:00 | Meeting | 17:00 | The goal of this journal is that each student writes the work done with its respective time spent.
| 2023-09-23 | Installation outils et composants requis | 2:00 | Preparation |  | This formally not asked by SCRUM, but useful to monitor the work of each student in the team.
| 2023-09-23 | Clone des projets Git fournis par les Product Owner | 2:00 | Preparation |  | Here are some example lines of the journal to illustrate it.
| 2023-09-30 | Daily Meeting | 0:30 | Meeting
| 2023-09-30 | Récupération du projet de base et tenter de le faire fonctionner | 2:00 | Preparation
| 2023-10-01 | Ajout du networking au projet avec un script pour tester | 2:00 | Dev
| 2023-10-07 | Daily Meeting + planning poker | 1:30 | Meeting
| 2023-10-14 | Daily Meeting | 2:00 | Meeting
| 2023-10-14 | Possibilité de tester plusieurs joueurs ajout d'interface pour se connecter en server, host,... debuguer le problème | 3:00 | Dev
etc. etc. etc.

## Student4 Journal
Name | Date | What | Time | Type | Total hours
| 2023-09-23 | Meeting avec les Product Owner et le Coach | 2:00 | Meeting | 17:00 | The goal of this journal is that each student writes the work done with its respective time spent.
| 2023-09-23 | Installation outils et composants requis | 2:00 | Preparation |  | This formally not asked by SCRUM, but useful to monitor the work of each student in the team.
| 2023-09-23 | Clone des projets Git fournis par les Product Owner | 2:00 | Preparation |  | Here are some example lines of the journal to illustrate it.
| 2023-09-30 | Daily Meeting | 0:30 | Meeting
| 2023-09-30 | Récupération du projet de base et tenter de le faire fonctionner | 2:00 | Preparation
| 2023-10-01 | Ajout du networking au projet avec un script pour tester | 2:00 | Dev
| 2023-10-07 | Daily Meeting + planning poker | 1:30 | Meeting
| 2023-10-14 | Daily Meeting | 2:00 | Meeting
| 2023-10-14 | Possibilité de tester plusieurs joueurs ajout d'interface pour se connecter en server, host,... debuguer le problème | 3:00 | Dev
etc. etc. etc.